## Slide 1
Supplemental Toolkit

## Slide 2
This toolkit is intended to provide practical country-level launch planning guidance to global health practitioners—built from private sector principles and public health best practices.
We have compiled these templates, examples, and tools to provide inspiration and guidance as you move through developing a scale-up strategy and operational launch plan. To help see how these tools might be used in practice, this guide contains:
    Illustrative, pre-populated tools based on the development of an operational launch plan for chlorhexidine (CHX) in Nigeria, and
    Blank tools that you can fill in as you develop your own operational launch plan
These tools are meant to serve as references to consider in helping you think through or address many of the questions and exercises identified in Ready, Set, Launch: A Country-Level Launch Planning Guide for Global Health Innovations. To that end, the toolkit is not exhaustive and is intended to be continually updated and refined over time with more examples and templates.
As such, we encourage your comments, new tools, and input at our website (www.usaid.gov/cii).
Let us know how we can make this better and more useful!
Overview of Supplemental Toolkit

## Slide 3
Step 1.1: Shortlist countries for launch
Country Prioritization Matrix Tool…5
Step 1.2: Finalize country selection
Country Prioritization Table Tool…7
Go/No-Go Checklist Tool…9
Step 2.1: Assess market and barriers
to scale
Stakeholder Mapping Tool…11
Market Assessment Tool…13
Barrier Assessment Tool…14
Market Segmentation Analysis Tool…19
Patient Journey Mapping Tool…21
Manufacturing Analysis Tool…23
Delivery Channel Analysis Tool…25
Clinical Trial Analysis Tool…31
Step 2.2: Develop strategy for overcoming barriers to scale-up
Comparable Product Analysis Tool…33
Intervention Design Tool…35
Step 3.1: Develop operational launch plan
Operational Launch Plan Tool…38
Cost Estimate Tool…40
Step 3.2: Set uptake targets and create monitoring plan
Monitoring and Evaluation Tool…42
Goals and Targets Tool…44
Country Dashboard Tool…46
M&E Framework Dictionary Tool…48
Tools available only in this Supplemental Toolkit
Table of Contents
Click to jump to Step 1: Ready?
Click to jump to Step 2: Set…
Click to jump to Step 3: Launch!
Note: All hyperlinks will only work in the ‘Slide Show’ mode.

## Slide 4
Step 1.1: Shortlist countries for launch
Country Prioritization Matrix Tool
Step 1.2: Finalize country selection
Country Prioritization Table Tool
Go/No-Go Checklist Tool
Tools available only in this Supplemental Toolkit
Ready? Select a Geography | Ready, Set, Launch STEP 1 2 3
1
Click to return to the
Table of Contents

## Slide 5
Chart: 
| 32 | 28 | 37 | 30 | 31 | 39 | 19 | 31 | 26 | 24 | 31 | 34 | 30 | 33 | 37 | 55 | 27 | 29 | 26 | 27 | 34 | 34
Y-Values | 0.71 | 0.187 | 0.885 | 0.414 | 0.605 | 0.59 | 0.327 | 0.552 | 0.401 | 0.644 | 0.22 | 0.408 | 0.408 | 0.574 | 0.622 | 0.472 | 0.21 | 0.267 | 0.482 | 0.398 | 0.839 | 0.517
Ready? Select a Geography | Ready, Set, Launch STEP 1 2 3
STEP 1.1 EXERCISE 1
Country Prioritization Matrix Tool
Short List of Countries
% of births that happen at home
Evaluation of country need based on neonatal mortality rate (NMR) and home births across USAID’s 24 priority countries
Larger market size countries:
Pakistan
Ethiopia
Yemen
Nigeria
India
Demonstration effect countries:
Haiti
Nepal
Kenya
Zambia
Analysis is limited to a select number of countries based on priorities
Short list of countries is split according to qualitative preferences
NMR
Analysis examines two quantifiable data points that are most relevant to the product
Illustrative
1
India2
Nigeria
Pakistan
Ethiopia
Bangladesh
Nepal
Kenya
Liberia
Madagascar
Malawi
Senegal
Mozambique
DRC
Indonesia
Rwanda
Mali
Ghana
Yemen
Haiti
Zambia
Tanzania
Uganda

## Slide 6
Ready? Select a Geography | Ready, Set, Launch STEP 1 2 3
Larger market size countries:
Country
Country
Country
Country
Country
Demonstration effect countries:
Country
Country
Country
Country
Data on y-axis
Data on x-axis
Evaluation of country need based on _ and _ across _ priority countries
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
x
x
x
x
x
x
x
x
x
x
STEP 1.1 EXERCISE 1
Country Prioritization Matrix Tool
Short List of Countries
1

## Slide 7
Ready? Select a Geography | Ready, Set, Launch STEP 1 2 3
STEP 1.2 EXERCISE 1
Country Prioritization Table Tool
Market Size
Feasibility1 (Measures of feasibility blend qualitative and quantitative information)
Country
Burden
Addressable market size
Bangladesh
3m
1m
Uganda
10m
2m
In-country relationships
Align with national priorities
Product on EML or related list
Product registered
Existing substitutes
Uptake of similar products
Overall feasibility2,3
4
7
Overall feasibility = (distribution mechanism) + (2 * payers) – (other products) + (.5 * substitutes)…
Overall feasibility formula will use simple math and favorably weight inputs that are more credible or that are better indicators of success
Note: (1) Use Harvey Balls to track feasibility variables with the exception of ‘overall feasibility.’ Other variables can be used as identified; (2) Roll up individual countries‘ feasibility variables to score overall on a scale of 1 (lowest feasibility) to 10 (highest feasibility); (3) Create bubble chart based on these two metrics.
Harvey Balls are visually easier to absorb but each rating can map back to a specific number
Market size will apply a limiting factor to the total population impacted by the disease/health issue to estimate the addressable market
Track feasibility vs. market size in a scorecard to populate underlying data for bubble chart
Measures of feasibility blend qualitative and quantitative information
Illustrative
1

## Slide 8
Ready? Select a Geography | Ready, Set, Launch STEP 1 2 3
STEP 1.2 EXERCISE 1
Country Prioritization Table Tool
Note: (1) Use Harvey Balls to track feasibility variables with the exception of ‘overall feasibility.’ Other variables can be used as identified; (2) Roll up individual countries‘ feasibility variables to score overall on a scale of 1 (lowest feasibility) to 10 (highest feasibility); (3) Create bubble chart based on these two metrics.
1
Overall feasibility = (distribution mechanism) + (2 * payers) – (other products) + (.5 * substitutes)…
Market Size
Feasibility1 (Measures of feasibility blend qualitative and quantitative information)
Country
Burden
Addressable market size
In-country relationships
Align with national priorities
Product on EML or related list
Product registered
Existing substitutes
Uptake of similar products
Overall feasibility2,3

## Slide 9
Ready? Select a Geography | Ready, Set, Launch STEP 1 2 3
STEP 1.2 EXERCISE 2
Go/No-Go Checklist Tool
1
If research during country selection identified any of these negative scenarios, evaluate the relative impact of the finding and reconsider scale-up and/or return to country selection to consider alternative countries.
Relevant no-go signals and principles
Example
Guidance on how to interpret signal
Mismatch between production economics and pricing potential
Price/production economics are higher than ability/willingness to pay, and economics cannot be improved
If production economics cannot be improved, and product necessitates end-user purchase (as opposed to donor funding), signal to reconsider
Signals of low demand
Poor uptake on similar products previously introduced in-country
If similar products have had poor uptake due to market/non-market factors that would similarly affect product, signal to reconsider
Challenging market dynamics/limited product differentiation
Product substitutes are priced lower and/or are more effective
If a substitute product is firmly entrenched, priced lower, and offers a similar value proposition, signal to reconsider
Lack of infrastructure to accommodate product needs
Product requirements can’t be met at point of delivery
If distribution and handling requirements (e.g., cold chain, nurse administration, etc.) can’t be met, strong signal to reconsider
Significant delays in country approval process
Regulatory signals suggest low likelihood of approval
If regulators pose skeptical questions in meetings, express doubt and present no solutions, signal to reconsider
Strong opposition to product entry from key decision makers
A key stakeholder wishes to block scale-up
If a senior government official or key opinion leader has expressed a strong objection to scale-up in their country, strong signal to reconsider
Core component
MARKET AND USER
MANUFACTURING AND DISTRIBUTION
CLINICAL EVIDENCE
AND REGULATORY
POLICY, ADVOCACY, AND FINANCING

## Slide 10
Step 2.1: Assess market and barriers
to scale
Stakeholder Mapping Tool
Market Assessment Tool
Barrier Assessment Tool
Market Segmentation Analysis Tool
Patient Journey Mapping Tool
Manufacturing Analysis Tool
Delivery Channel Analysis Tool
Clinical Trial Analysis Tool
Tools available only in this Supplemental Toolkit
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
Step 2.2: Develop strategy for overcoming barriers to scale-up
Comparable Product Analysis Tool
Intervention Design Tool
Click to return to the
Table of Contents

## Slide 11
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
STEP 2.1 EXERCISE 1
Stakeholder Mapping Tool
Group
Federal government
State government
Importance
Typical roles and responsibilities in scale-up
Government sets policy and oversees health programs and systems at the national level
Lead/coordinate efforts, set policy, conduct advocacy, provide funding
Government sets policy and oversees health programs and systems at the state level
Oversee implementation of scale-up activities at the state level, including procurement and distribution of product
Examples of stakeholders included
Department of Family Health, Department of Food and Drug Services
State ministries of health
Additional detail on capabilities, interests, and potential roles of key stakeholders
High-level visual to show key stakeholders driving product scale-up, mapped to depict key relationships and categories of interest (e.g., global, national, state, local)
Illustrative
Other stakeholders
[Continue for other stakeholders]
[Continue for other stakeholders]
[Continue for other stakeholders]
Other stakeholders
[Continue for other stakeholders]
[Continue for other stakeholders]
[Continue for other stakeholders]
Other stakeholders
[Continue for other stakeholders]
[Continue for other stakeholders]
[Continue for other stakeholders]
2

## Slide 12
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
STEP 2.1 EXERCISE 1 Stakeholder Mapping Tool
LOCAL
STATE
NATIONAL
GLOBAL
Other stakeholders
[Continue for other stakeholders]
[Continue for other stakeholders]
[Continue for other stakeholders]
Other stakeholders
[Continue for other stakeholders]
[Continue for other stakeholders]
[Continue for other stakeholders]
Other stakeholders
[Continue for other stakeholders]
[Continue for other stakeholders]
[Continue for other stakeholders]
Other stakeholders
[Continue for other stakeholders]
[Continue for other stakeholders]
[Continue for other stakeholders]
Other stakeholders
[Continue for other stakeholders]
[Continue for other stakeholders]
[Continue for other stakeholders]
2
USER
Group
Importance
Typical roles and responsibilities in scale-up
Examples of stakeholders included

## Slide 13
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
STEP 2.1 EXERCISE 2
Market Assessment Tool
2
Who is the target user?
Who influences the target user?
What is the point of care/point of access that is most relevant?
What competing products exist?
Key questions to ask a part of a market assessment
Will the product be supplied via local and/or global manufacturing?
What are the target delivery channels to reach target users (e.g., public, private)?
Are production economics in line with ability and willingness to pay?
What additional clinical evidence is needed?
What does the regulatory approval process require? How long does the process take?
Who is the target payer? What is their ability to pay? Willingness to pay?
What organizations have been involved in or provided resources for scale-up activities for similar activities in the past?
How much have scale-up interventions in the past cost?
What is the process for including the product in appropriate protocols/lists (e.g., essential medicines list, national (protocol)?
Who are ideal candidates to lead the launch and scale-up and/or serve the uptake coordinator role?
What entities have owned/managed interventions in the past? How long did these efforts take to carry out?
Core Component
MARKET AND USER
MANUFACTURING AND DISTRIBUTION
CLINICAL EVIDENCE
AND REGULATORY
POLICY, ADVOCACY, AND FINANCING
COORDINATION

## Slide 14
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
STEP 2.1 EXERCISE 3
Barrier Assessment Tool | Market and user
Evaluate target users’ current awareness of and demand for the product
Barrier
Barrier (color red, yellow, green)
Key considerations
Desired outcome
How to determine level of urgency
Target users/payers don’t see a need for the product
How have other sub-optimal health behaviors been improved?
Target users aren’t aware of the value of the product
How have other new products generated demand?
Target users do not know how to use the product
How have target users been trained for other products?
It is difficult to predict how much product is demanded
Target users understand the need for the product and, therefore, are more likely to seek out the product
Target users know about the product’s benefits and are motivated to access it
Target users know how and when to use the product, resulting in greater uptake of the product in the right circumstances
Accurate projections of market demand will aid in planning for sufficient supply and scale-up activities
Is the need for treatment known and/or are flaws of current treatment options recognized by the target user? If no, then red.
Do target users know about the product and want to access it? If no, then red.
Do target users know how and when to use the product? If no, then red
Can the target user easily access and understand instructions for use? If no, then red.
Are there well informed calculations that link coverage rates to total market demand for the product? If no, then red.
How quickly could consumer demand change in-country?
It is difficult to know where to set the price of the product
What portion of target users are currently priced-out?
The product and packaging design is confusing/unclear to users or gate-keepers
Product is priced appropriately based on target user affordability and business needs/costs
Product and packaging design reflects user-centered research to improve appeal and prevent improper usage
Is the product affordable to target users? If no, then red
Does the price provide a reasonable margin for manufacturers and other actors in the supply chain? If no, then red.
Is the product differentiated and attractive to targets? If no, then red.
Does packaging design lend itself to product misuse? If yes, then red.
Have there been reported cases of misuse? Does the product design resemble others, potentially creating confusion?
Provide details and cite how you determined the level of need and relevant implications for scale-up
Low barrier
Medium barrier
High barrier
Ratings are meant primarily to indicate relative barrier, and are more art than science
2

## Slide 15
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
STEP 2.1 EXERCISE 3
Barrier Assessment Tool | Manufacturing and distribution
Evaluate how to optimize the supply chain and which delivery channels to prioritize
Barrier
Key considerations
Desired outcome
How to determine level of urgency
There aren’t clear/functional delivery channels
How have similar products optimized delivery channels previously?
There aren’t incentives to integrate the product into existing delivery channels
What incentives have worked in moving global health product inventory in past scale-ups?
There aren’t local and/or global manufacturers willing or able to manufacture the product
What other products has this local or global manufacturer brought to market?
Supply for the product doesn’t meet demand forecasts
Functional procurement and distribution systems will link product supply to all points of access/target users
Public and private sector channels incentivize affordable, fast, and reliable delivery of the product to target users
Production strategy (including high-potential manufacturers) exists, and can meet scale-up needs
Production strategy includes a clear plan to support anticipated demand
Can the product be placed into the target delivery channels and assume it will flow seamlessly to target users? If no, then red.
Are there large bottlenecks in the delivery channels that will hinder the product’s movement to target users? If yes, then red.
Is there a local manufacturer that is already producing or ready to immediately produce or a global manufacturer ready to export to the country? If no, then red.
Do both demand and supply forecasts exist and is supply sufficient to cover demand? If no, then red.
What are future key points of inflection for manufacturing capacity?
Production economics don’t favor necessary margin requirements
Are there ways to lower COGS or increase price to make production economics more attractive?
Economics (e.g., pricing, COGS) are favorable to manufacturers and distributors in order to incentivize production and distribution of the product
Are the manufacturers able to make an attractive margin on the product? If no, then red.
Barrier (color red, yellow, green)
Low barrier
Medium barrier
High barrier
Ratings are meant primarily to indicate relative barrier, and are more art than science
2

## Slide 16
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
STEP 2.1 EXERCISE 3
Barrier Assessment Tool | Clinical and regulatory
Identify clinical data needed or any potential impact that new clinical data could have on scale-up
There are signals that additional clinical evidence is needed and/or would accelerate scale-up
Have other products in country benefitted from additional or updated clinical data?
Clinical studies/evidence are ongoing in target country and/or other countries
Would outcomes of active trials impact government acceptance of product?
Presenting additional clinical evidence from local trials or that present new data can expedite the approval process or expand the product’s approved uses
Additional evidence should be monitored to determine if the strategy should be adapted
Is regulatory approval contingent on additional clinical evidence? If yes, then red.
Are there active trials set to report data that could impact the current product registration or regulatory process? If yes, then red.
Low barrier
Medium barrier
High barrier
Ratings are meant primarily to indicate relative barrier, and are more art than science
2
Barrier
Key considerations
Desired outcome
How to determine level of urgency
Barrier (color red, yellow, green)

## Slide 17
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
STEP 2.1 EXERCISE 3
Barrier Assessment Tool | Policy, advocacy, and financing
Establish an enabling environment for scale-up
There isn’t sufficient commitment from KOLs
What professional associations are key to clinical adoption of the product?
The product doesn’t have placement on EML or other relevant lists, as needed
What lists are currently used at the point of access?
There is no clear buyer/payer for the product (if the user is not the buyer)
Will medium and long-term funding for scale-up require a shift in payers?
KOL buy-in can aid in policy makers and clinicians hearing about the benefits of the product
Inclusion in clinical lists elevates the product as a standard of care and ensure long term utilization at health facilities
Establishing funding beyond early activities certifies that momentum in scale-up can be maintained
Have policy makers spoken about the need for the product publicly? If no, then red.
Do most practitioners know about the clinical benefits of the product? If no, then red.
Are there clinical lists or purchasing ledgers that list a competing product/treatment as opposed to the product in question? If yes, then red.
Are there buyers/payers who have committed funds for short, medium, and long-term activities? If no, then red.
Low barrier
Medium barrier
High barrier
Ratings are meant primarily to indicate relative barrier, and are more art than science
2
Barrier
Key considerations
Desired outcome
How to determine level of urgency
Barrier (color red, yellow, green)

## Slide 18
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
STEP 2.1 EXERCISE 3
Barrier Assessment Tool | Coordination
Ensure appropriate ownership and execution of strategy over time
Barrier
There aren’t phasing plans in place
There aren’t clear roles and responsibilities for launch and scale of the product (depending on stage of scale-up process)
Supply and demand forecasts, and timing of supply and demand, aren’t defined or matched
There isn’t a clear, defined M&E dashboard
There are signs of an unhealthy market
Key considerations
Desired outcome
How to determine level of urgency
How have similar scale-up efforts phased resources?
Do key actors have geographic or functional preferences or strengths that can aid in assigning roles?
What is estimated supply capacity? Is it sufficient to cover demand?
Optimize limited resources for specific regions or channels so that ‘early wins’ provide demand and test interventions
Clear delineation of roles and responsibilities encourages follow through on implementation
Identify any potential volume imbalances between supply and demand today and in the future
Track progress against key milestones and optimize
Are resources limited relative to the human and financial capital required for interventions and coordination? If yes, then red.
Are there a large number of activities and actors, and very little precedent for coordination during scale-up? If yes, then red.
Do both demand and supply forecasts exist, and is supply sufficient to cover demand? If no, then red.
Have key metrics been identified? If no, then red. Are all stakeholders aligned? If no, then red.
How have similar scale-up efforts created dashboards? How can the metrics be kept lean?
How would the market react to a sudden change in supply or demand?
Identify any market trends that could undermine the long-term sustainability of the market
Will manufacturers continue to make an attractive margin on the product? If no, then red.
In smaller ‘test markets,’ did a steady state level of demand remain? If no, then red.
Barrier (color red, yellow, green)
Low barrier
Medium barrier
High barrier
Ratings are meant primarily to indicate relative barrier, and are more art than science
2

## Slide 19
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
Illustrative
Total Market
7.1M annual births in Nigeria
42%
58%
Facility
Home
Point of Delivery
88% of deliveries had purchased substance for cord care
Cord care Awareness
Target user/first applier of product
Nurse/Physician - 2.95M (42%)
Mother/Family - 2.21M (32%)
CHW/TBA - 1.85M (26%)
Includes:
Nurse/nurse midwife (28.8%)
Physician (12.2%)
Auxiliary nurse midwife (3.2%)
Includes:
Traditional birth assistant (TBA)/volunteer health worker (VHW) (20.8%)
Community health worker, e.g., CHW or CHEW (2.2%)
Midwives
Includes:
Mother (11.2%)
Family member, e.g., mother-in-law, sister, grandmother (20.3%)
= 1M births
= 500k deliveries
Provide the total potential market size, before filtering down to your product’s addressable market
After answering the who, what, where, and when for your product, base your first division on the most pronounced difference
If it simplifies the analysis, group similar roles together to be one target user
2
STEP 2.1
Market Segmentation Analysis Tool

## Slide 20
Total Market
Fill in total market size
%
%
x
x
Point of Delivery
Input here
Cord care Awareness
Target user/first applier of product
Group 1 - # (%)
Includes:
List down similar roles together
Provide the total potential market size, before filtering down to your product’s addressable market
After answering the who, what, where, and when for your product, base your first division on the most pronounced difference
If it simplifies the analysis, group similar roles together to be one target user
Group 2 - # (%)
Includes:
List down similar roles together
Group 3 - # (%)
Includes:
List down similar roles together
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
STEP 2.1
Market Segmentation Analysis Tool

## Slide 21
Illustrative
Facility-based health provider
Community health worker
Mother/family member
Three target users for product:
Target users become aware of product
Target users access product
KOLs within the facility
Training/education
KOLs within professional associations
Demand from patients
‘Mama kit’ lists
Advertisements via radio, posters, print
Facility - public or
private (42%)
Private pharmacy or PPMV
Early gatekeepers
Later reinforcement
Key influences:
Private facility
Public facility
Health providers at PHCs and/or facilities
Community leaders
Training/education
KOLs within professional associations
Demand from community members
‘Mama kit’ lists
Advertisements via radio or posters
Home - assisted by
non-family (26%)
Private pharmacy or PPMV
Private direct
Public pharmacy
Public direct
Point of service:
Point of access:
Community leaders
Community members, including other mothers
Health providers (e.g., recommendation during ANC visit)
‘Mama kit’ lists
Advertisements via radio or posters
Home – unassisted or assisted by family (32%)
Private pharmacy or PPMV
Private direct
Public pharmacy
Public direct
Awareness of the need for the product should be added when behavior change is necessary
This analysis assumes the perspective of target
Map point of service and access to each other if different
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
Public
Private
STEP 2.1
Patient Journey Mapping Tool

## Slide 22
Group 1
Group 2
Group 3
Three target users for product:
Target users become aware of product
Target users access product
List Here
List Here
Write here
Define here
Early gatekeepers
Later reinforcement
Key influences:
Define here
Define here
List Here
List Here
Write here
Define here
Define here
Define here
Define here
Point of service:
Point of access:
List Here
List Here
Write here
Define here
Define here
Define here
Define here
Awareness of the need for the product should be added when behavior change is necessary
This analysis assumes the perspective of target
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
Map point of service and access to each other if different
Public
Private
STEP 2.1
Patient Journey Mapping Tool

## Slide 23
Illustrative
Estimated capacity of local production of product
Millions of tubes per year, Q4 2015 to Q1 2016
115
180
10
5
0
15
20
5
Q1 2016
0
Q3 2015
0
8
5
21
118
21
21
177
Q4 2015
8
7
Project supply over time to account for any suppliers entering or leaving the market
Potential demand
25g tube
3g tube
21g tube
20g tube
Compare forecasts of supply and demand and report capacity by version of the product
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
Points of access
Distribution
Procurement
Manufacturing
STEP 2.1
Manufacturing Analysis Tool

## Slide 24
Estimated capacity of local production of product
Millions of _ per year, Q4 20__ to Q1 20__
Chart: 
 | 0 | 5096000 | 5096000
0
0
0
0
0
0
0
Q5
Q3
Q4
Project supply over time to account for any suppliers entering or leaving the market
KEY
Compare forecasts of supply and demand and report capacity by version of the product
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
Points of access
Distribution
Procurement
Manufacturing
STEP 2.1
Manufacturing Analysis Tool

## Slide 25
Illustrative
Points of access
Distribution
Procurement
Manufacturing
Public pharmacy
Public direct
Private pharmacy or PPMV
Private direct
Direct to government via state warehouses
Third party contractor
State government
Donors
Direct to government via state warehouses
Third party contractor
Direct to government
Direct to hospital
Third party contractor
State government
Public hospitals
Donors
Direct to government
Third party contractor
Donors
State government
Public facility
Independent distributor
Open drug markets
Independent distributor
Direct to hospital
Independent distributor
Open drug markets
Independent distributor
Private hospitals
Independent distributor
Independent distributor
Private facility
Separate procurement roles from distribution roles, even if there’s overlap in actors
Split past or future sales across relevant channels
Highlight when product transfers require payment
Local manufacturing
As of Q4 2015, Drugfield has sold 1.04 million tubes of product in Nigeria
78%
to public sector
22%
to private sector
$
$
$
$
$
$
$
$
$
$
$
$
$
$
$
$
$
$
$
Public
Private
Requires payment
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
STEP 2.1
Delivery Channel Analysis Tool (1/3)

## Slide 26
Illustrative
Each state should evaluate which existing channels are best suited for the product, noting that:
Channels used in each state are often product-specific (e.g., MNCH, family planning)
Many states are working to integrate and harmonize current channels
Direct to hospital
Suppliers have dedicated sales representatives tasked with clinical advocacy at private and public (secondary and tertiary) hospitals
Independent distributors
Suppliers sell to independent distributors who later resell
Third party contractor
Suppliers contract independent firm specializing in the distribution of consumer and other goods through a propriety distribution system; most common in public sector
Public
Private
Direct to government
Suppliers compete in government tenders and supply directly from their central or regional warehouse to the state central medical store
Informal
Pooled procurement of PPMVs
Community-based distribution
Vertically-integrated
Suppliers operate central or regional warehouse connected to distribution network of wholesalers/distributors
Unregulated open drug markets
Up to 80% of drugs on market pass through
Provide details on where product is warehoused, sent to, and sourced from
Differences in how regulated the point of distribution is can be highlighted if relevant
v
$
Public
Private
Requires payment
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
Points of access
Distribution
Procurement
Manufacturing
STEP 2.1
Delivery Channel Analysis Tool (2/3)

## Slide 27
FMoH and donors play catalytic role to subsidize cost of the product for state-led procurement
% private sector procurement
Goal split between public vs. private procurement
% private sector procurement, 2015 to 2025
Illustrative
Identify who the likely purchaser will be in your ‘exit strategy’ and how procurement will shift over scale-up
v
States start procuring the product, incentivized by commodity subsidy
Private sector procurement increases over time, motivated by public sector demand
In the long term, state-level public and private procurement balance out to match distribution of private/public points of access for the product
If the product requires subsidization, identify for how long and what the long-term goal for procurement is
v
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
Points of access
Distribution
Procurement
Manufacturing
STEP 2.1
Delivery Channel Analysis Tool (3/3)

## Slide 28
Point of access 1
Point of access 3
Point of access 4
Point of access 6
List here
List here
Direct to government via state warehouses
Third party contractor
List here
List here
List here
List here
Point of access 2
List here
List here
List here
List here
List here
List here
Point of access 5
Separate procurement roles from distribution roles, even if there’s overlap in actors
Split past or future sales across relevant channels
Highlight when product transfers require payment
Local manufacturing
Please specify
%
to public sector
%
to private sector
$
$
$
$
$
$
$
$
$
$
$
$
$
$
$
$
$
$
$
Public
Private
Requires payment
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
Points of access
Distribution
Procurement
Manufacturing
STEP 2.1
Delivery Channel Analysis Tool (1/3)

## Slide 29
Each state should evaluate which existing channels are best suited for the product, noting that:
Channels used in each state are often product-specific (e.g., xx)
Many states are working to integrate and harmonize current channels
List here
xx
List here
xx
List here
xx
Public
Private
List here
xx
List here
xx
List here
xx
List here
xx
Provide details on where product is warehoused, sent to, and sourced from
Differences in how regulated the point of distribution is can be highlighted if relevant
v
$
Public
Private
Requires payment
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
Points of access
Distribution
Procurement
Manufacturing
STEP 2.1
Delivery Channel Analysis Tool (2/3)

## Slide 30
_ catalytic role to subsidize cost of the product for state-led procurement
Chart: 
| 2015.0000000002301 | 2020.0000000002301 | 2025.0000000002301
 | 22 | 65 | 65
% private sector procurement
Goal split between public vs. private procurement
% private sector procurement, 20__ to 20__
Identify who the likely purchaser will be in your ‘exit strategy’ and how procurement will shift over scale-up
v
_incentivized by commodity subsidy
_increases over time, motivated by public sector demand
In the long term, _ public and private procurement balance out to match distribution of private/public points of access for the product
If the product requires subsidization, identify for how long and what the long-term goal for procurement is
v
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
Points of access
Distribution
Procurement
Manufacturing
STEP 2.1
Delivery Channel Analysis Tool (3/3)

## Slide 31
Illustrative
Lancet
2006
24% reduction in newborn mortality
CHW application for home births
Country
Journal
Year
Findings
NEPAL
BANGLADESH
PAKISTAN
META-ANALYSIS
Lancet
2012
20% reduction in newborn mortality
Cord cleansing on first day of birth
Lancet
2012
40% reduction in newborn mortality
The product provided by traditional birth attendants
BMC Public Health
2013
23-40% reduction in newborn mortality
The product provided by traditional birth attendants
UPDATE
Clinical study in India is now underway to attain local data to support advocacy and accelerate introduction timeline (BMGF, SNL)
Clinical studies in Tanzania and Zambia are complete and pending results
Provide updates on active clinical trials
Present academic literature and trials to date with key findings
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
STEP 2.1
Clinical Trial Analysis Tool

## Slide 32
Illustrative
Country
Journal
Year
Findings
COUNTRY 1
COUNTRY 2
COUNTRY 3
META-ANALYSIS
Present academic literature and trials to date with key findings
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
STEP 2.1
Clinical Trial Analysis Tool
UPDATE
x
Provide updates on active clinical trials

## Slide 33
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
Comparable products
ORS/Zinc
Misoprostol
Estimated cost
Activity
Estimated cost
Because of the large target user base a national marketing plan was disseminated through radio and print
Key intervention was sensitized with community leaders
Bundled other maternal and child health products with
misoprostol to drive demand
$50,000
Demand generation
$10,000
Care-seeking behavior for diarrhea was fragmented so awareness was driven through clinicians and retailers
Introduced expecting mothers to product at ANC visits
$15,000
Creating awareness
$1,000
Care-seeking behavior for diarrhea was fragmented so awareness was driven through clinicians and retailers
Focused training on community midwives and community-based health volunteers
$10,000
Training and education
$10,000
Market and user
Used training and detailing at points of retail to encourage shop owners to improve stocking practices and increase inventory turns
Community sensitization required meeting with community and religious leaders
$5,000
Delivery channel incentives
$2,000
Encouraged manufacturers to enter the market and then provided a COGS analysis to manufacturers who were committed to decreasing price
Affordable imported product; >50 branded and non-branded versions available globally
$3,000
Production economics
$1,000
Manufacturing
and distribution
[Additional core components]
Illustrative
Description of intervention used
Description of intervention used
cost
Additional activity…
cost
Description of intervention used
Description of intervention used
cost
Additional activity…
cost
2
Use these interventions as starting points for a long list of interventions that are most relevant to the target product
Select comparable products that have similar target users, delivery channels, and price to ensure relevant insights
Organize relevant information according to the key activities required
STEP 2.2 EXERCISE 1
Comparable Product Analysis Tool

## Slide 34
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
2
Comparable products
Product 1
Product 2
Estimated cost
Activity
Estimated cost
Market and user
Manufacturing
and distribution
[Additional core components]
STEP 2.2 EXERCISE 1 Comparable Product Analysis Tool

## Slide 35
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
Recommended interventions + potential associated activities
Low awareness at points of access for target users
Barrier
Conduct clinical mentoring and training activities at public and private facilities, leveraging professional associations for many of the private sector visits and state ministries of health (SMoHs) at select public and private facilities to demonstrate commitment and secure buy-in
Manufacturers, implementers, SMoHs, facility directors, professional associations
Conduct training activities at private pharmacies and public pharmacies at PHCs, leveraging professional associations for many of the private sector visits and SMoHs at select public and private pharmacies to demonstrate commitment and secure buy-in; consider clinical mentoring at primary health centers
Manufacturers, implementers, SMoHs, PHC directors, professional associations
Conduct training activities for donors and private companies currently distributing delivery/Mama kits or considering this work in the future
Implementers, SMoHs
Support states with their forecasts
Compile state projections for demand into a forecast and check against scale-up plan targets as well as realistic limitations (e.g., available funding)
Update forecast annually
Uptake coordinator for national forecasts and aggregating state forecasts
States/implementers for state forecasts, with support of uptake coordinator, as needed
Facilities
Pharmacies
Direct
Lack of aggregated demand forecasts
Potential stakeholder responsible
Illustrative
If multiple activities are tied to the barrier they should map back to specific roles and identify if those roles are national or sub-national
2
Market and user
[Additional core components]
List appropriate barriers according to the core components of scaling here…
Think through detailed intervention…
Determine responsible party…
STEP 2.2 EXERCISE 2 Intervention Design Tool

## Slide 36
Set…Build a Strategy | Ready, Set, Launch STEP 1 2 3
Recommended interventions + potential associated activities
List appropriate barriers according to the core components of scaling here…
Barrier
Potential stakeholder responsible
2
COORDINATION
List appropriate barriers according to the core components of scaling here…
List appropriate barriers according to the core components of scaling here…
List appropriate barriers according to the core components of scaling here…
List appropriate barriers according to the core components of scaling here…
MANUFACTURING and DISTRIBUTION
MARKET AND USER
CLINICAL EVIDENCE
and REGULATORY
POLICY, ADVOCACY, and FINANCING
STEP 2.2 EXERCISE 2 Intervention Design Tool

## Slide 37
Step 3.1: Develop operational launch plan
Operational Launch Plan Tool
Cost Estimate Tool
Step 3.2: Set uptake targets and create monitoring plan
Monitoring and Evaluation Tool
Goals and Targets Tool
Country Dashboard Tool
M&E Framework Dictionary Tool
Tools available only in this Supplemental Toolkit
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
3
Click to return to the
Table of Contents

## Slide 38
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
STEP 3.1 EXERCISE 1
Operational Launch Plan Tool
3
Months after launch
Timeline to show overall sequencing of activities for strategic interventions across the five core components of scale-up
0 – 3
3 – 6
6 – 12
12 – 24
Release messaging materials
Complete national and state demand forecasts
Create fund to subsidize 75% commodity cost
Start disbursing funds to states
Oversee efforts to subsidize 75% commodity costs for states launching programs
Expand private sector delivery channels
Monitor evidence from future studies
Close funding gap for scale-up plan
Conduct in-person advocacy visits to hospitals
Send representative to promote product at all relevant professional association conferences
Add product to EML/relevant lists
Conduct M&E activities
Finalize M&E system
Formalize coordinating mechanism
Host coordination meetings (monthly for the first year, quarterly thereafter)
Update phasing strategy each quarter
Owner
Activity
Timeframe
Strategy
Cost (USD)
Donors
Improve packaging and branding for product
6-12 months
1 – Market user
MoH
Release messaging materials
0-3 months
1 – Market user
MoH
Update and disseminate training materials
0-3 months
1 – Market user
MoH
Create fund to subsidize 75% commodity cost
0-3 months
2 - Manufacturing and distribution
MoH
Start disbursing funds to states
200,000
Covered by existing staff
10,000
580,000
Covered by existing staff
0-6 months
2 - Manufacturing and distribution
Table to enumerate all activities with clear owner, cost, and timeframe; if helpful, table can also include sub-activities
Illustrative
MARKET AND USER
MANUFACTURING AND DISTRIBUTION
CLINICAL EVIDENCE
AND REGULATORY
POLICY, ADVOCACY, AND FINANCING
COORDINATION

## Slide 39
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
Months after launch
3
0 – 3
3 – 6
6 – 12
12 – 24
Owner
Activity
Timeframe
Strategy
Cost (USD)
MARKET AND USER
MANUFACTURING AND DISTRIBUTION
CLINICAL EVIDENCE
AND REGULATORY
POLICY, ADVOCACY, AND FINANCING
COORDINATION
STEP 3.1 EXERCISE 1
Operational Launch Plan Tool

## Slide 40
Illustrative
Total scale-up costs required
Projected $ spend (millions), years 1-5
Chart: 
 | 1050000 | 1342750 | 2269500 | 2238500 | 2238500
 | 476631.1 | 257000 | 433000 | 221500 | 137250
 | 0 | 0 | 0 | 0 | 0
 | 411743.04 | 462854.72 | 655339.9 | 819195.28 | 893166.3
 | 3202310.92 | 3630236.87 | 5534623.42 | 3798854.43 | 2127556.85
9
1
8
5
7
2
6
4
3
$ (millions)
$7
$5
Year 5
Year 4
Year 3
Year 1
Year 2
$6
$9
$5
1 - Market and user
2 - Manufacturing and distribution
4 - Policy, advocacy, and financing
5 - Coordination
3 – Clinical evidence and regulatory
Aggregate year by year costs provide a skyline view of costs over the scale-up period
Primary drivers of costs:
Market and user – This strategy accounts for ~60% of total costs and the vast majority of that spend is required at the state level to kick start demand
Manufacturing and distribution – This strategy’s costs are largely associated with the procurement and distribution of CHX; activities will be designed to incentivize state-level actors to procure and distribute CHX
Clinical evidence and regulatory – No specific interventions are currently costed
Policy, advocacy, and financing – In the first two years, these costs focus on updating state EMLs, as well as advocacy trips conducted throughout the five years of the implementation plan
Coordination – The majority of coordination costs are incurred at the state-level for recurrent M&E activities
Accelerated/high investment scenario
Consider analyzing multiple scenarios for costing to get a reliable range
Commentary by core component highlight the key drivers of costs
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
3
See costing spreadsheet tool in Excel for sample costing template
STEP 3.1
Cost Estimate Tool

## Slide 41
Illustrative
Total scale-up costs required
Projected $ spend (millions), years 1-5
Chart: 
 | 0 | 0 | 0 | 0 | 0
9
1
8
5
7
2
6
4
3
$ (millions)
Year 5
Year 4
Year 3
Year 1
Year 2
1 - Market and user
2 - Manufacturing and distribution
4 - Policy, advocacy, and financing
5 - Coordination
3 – Clinical evidence and regulatory
Aggregate year by year costs provide a skyline view of costs over the scale-up period
Primary drivers of costs:
Market and user – xx
Manufacturing and distribution – xx
Clinical and regulatory – xx
Policy, advocacy, and financing – xx
Coordination – xx
Accelerated/high investment scenario
Consider analyzing multiple scenarios for costing to get a reliable range
Commentary by core component highlight the key drivers of costs
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
3
STEP 3.1
Cost Estimate Tool
See costing spreadsheet tool in Excel for sample costing template

## Slide 42
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
STEP 3.2 EXERCISE 1
Monitoring and Evaluation Tool
Target users correctly apply CHX
% of newborns (live births) that received first application of CHX gel to the umbilical cord at birth (home and facility births)
% of women with a live birth in the last two/five years who reported applying no substance other than CHX gel on the umbilical cord
% of health providers who recommended the use of CHX gel
% of skilled birth attendants having comprehensive knowledge and correct skills on CHX gel use and application
CHX is available to all target users
% of health facilities that provide maternity services with CHX gel stock-out in the last 3 months
% of PCN registered retail outlets (PPMVs and community/private pharmacists) with CHX gel stock-out in the last 3 months
CHX use follows latest clinical evidence and regulatory guidelines
% of health facilities that have copies of updated national protocols (STG, SOPs, Standing order)
No. of published in-country studies on CHX.
Policies, KOLs, and financing increase use of CHX
No. of states with budget line for CHX gel
No. of states with at least one development partner supporting CHX scale-up
CHX gel incorporated in published national EML (Y/N)
CHX gel incorporated in published national STG (Y/N)
No. of states with CHX gel on state EML
No. of states that procured and distributed CHX gel
CHX included as agenda item in national child health working group (Y/N)
Output
Outcomes
Providers are trained to use CHX correctly
No. of people trained on use and application CHX gel
Production and distribution of CHX is sufficient to meet demand
No. of CHX gel tubes produced
No. of CHX gel tubes distributed
Bi-annual CHX coordination stakeholder meetings occurred (Y/N)
CHX is widely promoted
No. of community mobilization activities held to promote CHX gel use
No. of slots for CHX adverts aired
Identify the epidemiological impact(s) your product will have
Pick outcome metrics that are closely correlated to your desired impact
Pick output metrics that provide effective ways to monitor that your scale-up efforts are on track
Illustrative
Impact
NMR
Coordination
3
MARKET AND USER
MANUFACTURING AND DISTRIBUTION
CLINICAL EVIDENCE AND REGULATORY
POLICY, ADVOCACY, AND FINANCE
COORDINATION

## Slide 43
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
Output
Outcomes
Impact
MARKET AND USER
MANUFACTURING AND DISTRIBUTION
CLINICAL EVIDENCE AND REGULATORY
POLICY, ADVOCACY, AND FINANCE
Coordination
3
COORDINATION
STEP 3.2 EXERCISE 1
Monitoring and Evaluation Tool

## Slide 44
Highlight key details from the most likely scenario
Illustrative
52
15
Year 3
Year 2
Year 5
Year 4
Year 1
% CHX coverage
Year 0
High/accelerated investment
Low/delayed investment
Medium investment
Projected CHX scale-up across three investment scenarios
% national coverage, years 0-5
Most likely scenario
Projections for accelerated scenario highlight:
All states have begun scale-up by the beginning of year three, resulting in straight line projections
The peak projected five-year coverage (~52%) is driven by application of CHX in facility and non-facility births, but the facility uptake curve outpaces the non-facility uptake curve
Ultimately coverage will depend on:
Ability of all states to execute
Access to required funding
Acknowledge key assumptions and/or factors that influence targets
Include graph that shows projected coverage over the time period of interest. If relevant, include targets for various scenarios (e.g., varying levels of funding).
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
3
STEP 3.2
Goals and Targets Tool

## Slide 45
Chart: 

Year 3
Year 2
Year 5
Year 4
Year 1
% CHX coverage
Year 0
High/accelerated investment
Low/delayed investment
Medium investment
Projected ___ scale-up across three investment scenarios
% national coverage, years 0-X
Most likely scenario
Projections for accelerated scenario highlight:
List here
Ultimately coverage will depend on:
List here
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
3
STEP 3.2
Goals and Targets Tool

## Slide 46
Illustrative
Percentage of newborns (live births) that received first application of CHX gel to the umbilical cord at birth (home and facility births)
Percentage of women with a live birth in the last two/five years who report applying no substance other than CHX gel to the cord
Percentage of health providers who recommended the use of CHX gel
Neonatal mortality rate
Year 1
Year 2
Year 3
Year 4
Year 5
Status
Status of each indicator can be updated at regular intervals (e.g., each quarter)
National dashboard includes key metrics to track over time; supporting pages can contain additional metrics to track at the national or subnational levels
Binary metrics:
Product approved by local regulatory authority
Product included in national EML and National Procurement List
Product included in national STG
Behind targets
Ahead of targets
Meeting targets
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
3
32
32
30
29
27
8%
15%
27%
40%
52%
5%
10%
20%
25%
29%
10%
15%
20%
30%
40%
STEP 3.2
Country Dashboard Tool

## Slide 47
Illustrative
Year 1
Year 2
Year 3
Year 4
Year 5
Status
Status of each indicator can be updated at regular intervals (e.g., each quarter)
National dashboard includes key metrics to track over time; supporting pages can contain additional metrics to track at the national or subnational levels
Binary metrics:
Product approved by local regulatory authority
Product included in national EML and National Procurement List
Product included in national STG
Behind targets
Ahead of targets
Meetings target
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
3
STEP 3.2
Country Dashboard Tool

## Slide 48
Illustrative
1
2
3
4
SN
Indicator
Measurement
Type
Data Source
Collection Method
Geographic Focus
Disaggregation
Reporting Frequency
Neonatal Mortality Rate
Percentage of newborns (live births) that received first application of CHX gel to the umbilical cord at birth (home and facility births)
Percentage of women with a live birth in the last two/five years who report applying no substance other than CHX gel to the cord
Percentage of health providers who recommended the use of CHX gel
Numerator: Number of deaths within first month of life.
Denominator: Total number of live births in the same year.
Unit of measurement: Rate (per 1,000 live births)
Numerator: Number of newborns that received first application of CHX gel on the umbilical cord at birth
Denominator: Total live births
Unit of measurement: Percentage
Numerator: Number of women 15-49 years with a live birth in the last two/five years who report applying no substance other than CHX gel to the cord
Denominator: Total number of live births
Unit of measurement : Percentage
Numerator: Number of health providers who reported recommending the use of CHX
Denominator: Total number of health providers and caregivers interviewed
Unit of measurement: Percentage
Impact
Outcome
Outcome
Outcome
NDHS
NDHS
SMART
HMIS LDR
NDHS
SMART
ISS
SMART
Report review
Report review
Report review
Interview
National
National
Geo-political zones
State
National
State
Sex
Geopolitical zones
State
State
Place of delivery
Level of facility
State
Place of delivery
State
LGA
Level of Facility
End line
Every five years
Annually
Quarterly
Monthly
Every five years
Annually
Quarterly
Biannually
Annually
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
3
STEP 3.2
M&E Framework Dictionary Tool

## Slide 49
Illustrative
1
2
3
4
SN
Indicator
Measurement
Type
Data Source
Collection Method
Geographic Focus
Disaggregation
Reporting Frequency
Launch! Plan for Scale-Up | Ready, Set, Launch STEP 1 2 3
3
STEP 3.2
M&E Framework Dictionary Tool